## Sheet1
PROJECT NAME: WEBSITE
CLIENT: Carolina Becerra - "Do Everything Salon" - Scenario 1
DATE: March 18, 2013
ADMINISTRATION | ESTIMATED HOURS | ACTUAL HOURS | DAYS - 8 hours
Initial meeting | 2
Meeting 2 | 1.5
Meeting 3 | 1.5
Meeting 4 | 1.5
Final Presentation | 1.5
Estimating | 3
Estimating contractors (contacting) | 3
Sending reports (meeting recaps) | 4
Billing | 2
SUBTOTAL: administration | 20 | 0 | 0
DIGITAL & GRAPHIC DESIGN COMPONENTS | EXISTING | QUANTITY | HOURLY RATE | ESTIMATED HOURS | ESTIMATED COST | DAYS - 8 hours | ACTUAL HOURS | BILLED | DAYS - 8 hours
Research | yes and no | 1 | 60 | 16 | 960
SUBTOTAL: digital & graphic design components |  |  |  | 16 | 960
DIGITAL COMPONENT | EXISTING | QUANTITY | HOURLY RATE | ESTIMATED HOURS | ESTIMATED COST | DAYS - 8 hours | ACTUAL HOURS | BILLED | DAYS - 8 hours
Information architecture | no | 1 | 60 | 6 | 360
Researching URL (client could take this on) | no | 1 | 60 | 1 | 60
Register URL (client could take this on) | no | 1 | 60 | 1 | 60
Securing URL | no | 1 | 60 | 1 | 60
Securing Service Provider | no | 1 | 60 | 1 | 60
Negotiating hosting rates | no | 1 | 60 | 3 | 180
Data base management (dedicated person) | no | 1 | 60 | 6 | 360
Data base compilation (dedicated person) | no | 1 | 60 | 4 | 240
Sourcing template | no | 1 | 60 | 4 | 240
Any additional custom coding | no | 1 | 60 | 20 | 1200
User testing | no | 1 | 60 | 7 | 420
Revisions 1 | no | 1 | 60 | 4 | 240
Revisions 2 | no | 1 | 60 | 2 | 120
SUBTOTAL: digital component |  |  |  | 60 | 3600 | 0 | 0 | 0 | 0
DIGITAL COMPONENT PHASE 2 | EXISTING | QUANTITY | HOURLY RATE | ESTIMATED HOURS | ESTIMATED COST | DAYS - 8 hours | ACTUAL HOURS | BILLED | DAYS - 8 hours
Online shopping back end, including shopping cart check-out (Phase 2) | no | 1 | 60 | 7 | 420
Virtual makeover back end (Phase 2) | no | 1 | 60 | 7 | 420
Appointment booking back end (Phase 2) | no | 1 | 60 | 4 | 240
Email form back end (Phase 2) | no | 1 | 60 | 3.5 | 210
SUBTOTAL: digital component PHASE 2 |  |  |  | 21.5 | 1290 | 0 | 0 | 0 | 0
DIGITAL DESIGN COMPONENT
Landing page (temporary "splash" page) | no | 1 | 60 | 4 | 240
Website template design | no | 5 | 60 | 16 | 960
Copywriting | no | 1 | 60 | 10 | 600
Copy editing/proofreading | no | 1 | 60 | 6 | 360
Images | yes | 12 | n/a | n/a | n/a
Image retouching or resizing | no | 12 | 60 | 8 | 480
SUBTOTAL: digital design component PHASE 1 |  |  |  | 40 | 2640 | 0 | 0 | 0 | 0
DIGITAL DESIGN COMPONENT PHASE 2
Design of online shopping page (Phase 2) | no | 1 | 60 | 8 | 480
Design of virtual makeover (Phase 2) | no | 1 | 60 | 9 | 540
Design of online appointment booking (Phase 2) | no | 1 | 60 | 6 | 360
Design of email form (Phase 2) | no | 1 | 60 | 4 | 240
SUBTOTAL: digital design component PHASE 2 |  |  |  | 27 | 1620 | 0 | 0 | 0 | 0
GRAPHIC DESIGN COMPONENT
Brand identity (logo, colour palette, fonts, any brand graphics, stationery) | no | 1 | 90 | 45 | 4050
Copywriting (mission, tagline) | no | 1 | 65 | 5 | 325
Design four ads | no | 4 | 60 | 6 | 360
Revisions 1 | no | 1 | 60 | 7 | 420
Revisions 2 | no | 1 | 60 | 4 | 240
SUBTOTAL: graphic design component |  |  |  | 67 | 5395 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 183 | 15505