## Sheet1
PROJECT NAME: WEBSITE
CLIENT: Carolina Becerra - "Do Everything Salon" - Scenario 1
DATE: March 18, 2013
ADMINISTRATION | ESTIMATED HOURS | ACTUAL HOURS | DAYS - 8 hours
Initial meeting | 2
Meeting 2 | 1.5
Meeting 3 | 1.5
Meeting 4 | 1.5
Final Presentation | 1.5
Estimating | 3
Estimating contractors (contacting) | 3
Sending reports (meeting recaps) | 4
Billing | 2
SUBTOTAL: administration | 20 | 0 | 0
DIGITAL & GRAPHIC DESIGN COMPONENTS | EXISTING | QUANTITY | HOURLY RATE | ESTIMATED HOURS | ESTIMATED COST | DAYS - 8 hours | ACTUAL HOURS | BILLED | DAYS - 8 hours
Research | yes and no | 1 | 60 | 16 | 960
SUBTOTAL: digital & graphic design components |  |  |  | 16 | 960
DIGITAL COMPONENT | EXISTING | QUANTITY | HOURLY RATE | ESTIMATED HOURS | ESTIMATED COST | DAYS - 8 hours | ACTUAL HOURS | BILLED | DAYS - 8 hours
Information architecture | no | 1 | 60 | 6 | 360
Researching URL (client could take this on) | no | 1 | 60 | 1 | 60
Register URL (client could take this on) | no | 1 | 60 | 1 | 60
Securing URL | no | 1 | 60 | 1 | 60
Securing Service Provider | no | 1 | 60 | 1 | 60
Negotiating hosting rates | no | 1 | 60 | 3 | 180
Data base management (dedicated person) | no | 1 | 60 | 6 | 360
Data base compilation (dedicated person) | no | 1 | 60 | 4 | 240 | Data base creation can be quiet an extensive job, depending on the size of it, complexity and management. An item like this would require from what i've seen, at least one solid work week. But maybe it is not necessary for this stage of this project. Same comment with user testing, online shopping back end,and most of the stuff in phase 2. You'll be able to estimate this better once you've done it
Sourcing template | no | 1 | 60 | 4 | 240
Any additional custom coding | no | 1 | 60 | 20 | 1200
User testing | no | 1 | 60 | 7 | 420
Revisions 1 | no | 1 | 60 | 4 | 240
Revisions 2 | no | 1 | 60 | 2 | 120
SUBTOTAL: digital component |  |  |  | 60 | 3600 | 0 | 0 | 0 | 0
DIGITAL COMPONENT PHASE 2 | EXISTING | QUANTITY | HOURLY RATE | ESTIMATED HOURS | ESTIMATED COST | DAYS - 8 hours | ACTUAL HOURS | BILLED | DAYS - 8 hours
Online shopping back end, including shopping cart check-out (Phase 2) | no | 1 | 60 | 7 | 420
Virtual makeover back end (Phase 2) | no | 1 | 60 | 7 | 420
Appointment booking back end (Phase 2) | no | 1 | 60 | 4 | 240
Email form back end (Phase 2) | no | 1 | 60 | 3.5 | 210
SUBTOTAL: digital component PHASE 2 |  |  |  | 21.5 | 1290 | 0 | 0 | 0 | 0
DIGITAL DESIGN COMPONENT
Landing page (temporary "splash" page) | no | 1 | 60 | 4 | 240
Website template design | no | 5 | 60 | 16 | 960
Copywriting | no | 1 | 60 | 10 | 600
Copy editing/proofreading | no | 1 | 60 | 6 | 360
Images | yes | 12 | n/a | n/a | n/a
Image retouching or resizing | no | 12 | 60 | 8 | 480
SUBTOTAL: digital design component PHASE 1 |  |  |  | 40 | 2640 | 0 | 0 | 0 | 0
DIGITAL DESIGN COMPONENT PHASE 2
Design of online shopping page (Phase 2) | no | 1 | 60 | 8 | 480
Design of virtual makeover (Phase 2) | no | 1 | 60 | 9 | 540
Design of online appointment booking (Phase 2) | no | 1 | 60 | 6 | 360
Design of email form (Phase 2) | no | 1 | 60 | 4 | 240
SUBTOTAL: digital design component PHASE 2 |  |  |  | 27 | 1620 | 0 | 0 | 0 | 0
GRAPHIC DESIGN COMPONENT
Brand identity (logo, colour palette, fonts, any brand graphics, stationery) | no | 1 | 90 | 45 | 4050
Copywriting (mission, tagline) | no | 1 | 65 | 5 | 325
Design four ads | no | 4 | 60 | 6 | 360
Revisions 1 | no | 1 | 60 | 7 | 420
Revisions 2 | no | 1 | 60 | 4 | 240
SUBTOTAL: graphic design component |  |  |  | 67 | 5395 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 183 | 15505