## Sheet1
PROJECT NAME: WEBSITE
CLIENT: Carolina Becerra - Do EVERYTHING Salon
DATE:
ADMINISTRATION | ESTIMATED HOURS | ACTUAL HOURS | enter in DAYS (8hr)
Initial meeting | 2
Meeting 2 | 1.5
Meeting 3 | 1.5
Meeting 4 | 1.5
Final Presentation | 1.5
Estimating | 3
Estimating contractors | 3
Sending Reports (are reports project updates?) | 4
Billing | 2
DIGITAL & GRAPHIC DESIGN COMPONENTS | EXISTING | QUANTITY | HOURLY RATE | ESTIMATED HOURS | ESTIMATED COST | DAYS (8hr) | ACTUAL HOURS | BILLED | DAYS (8 hr)
Market and other research | no | 1 | 60 | 15 | 900
DIGITAL COMPONENT | EXISTING | QUANTITY | HOURLY RATE | ESTIMATED HOURS | ESTIMATED COST | DAYS (8hr) | ACTUAL HOURS | BILLED | DAYS (8 hr)
architectural map | no | 1 | 60 | 6 | 360
landing page | no | 1 | 60 | 6 | 360
researching URL | no | 1 | 60 | 1 | 60
Register URL | no | 1 | 60 | 1 | 60
Securing URL | no | 1 | 60 | 1 | 60
Securing Service Provider | no | 1 | 60 | 2 | 120
Negotiating hosting rates | no | 1 | 60 | 3 | 180
Data base management | n/a | n/a | n/a | n/a | n/a
Data base compilation | no | 1 | 60 | 4 | 240
Sourcing template | no | 1 | 60 | 3 | 180
Coding from scratch | no | 1 | 60 | 20 | 1200
User testing | no | 1 | 60 | 8 | 480
Appointment booking back end | no | 1 | 60 | 4 | 240
Appointment booking front end | no | 1 | 60 | 8 | 480
Virtual makeover front end | no | 1 | 60 | 6 | 360
Virtual makeover back end | no | 1 | 60 | 8 | 480
Email front end | no | 1 | 60 | 4 | 240
Email back end | no | 1 | 60 | 4 | 240
Contractor (schedules, etc) | no | 1 | 60 | 6 | 360
revisions 1 | included | 1 | 60 | 6 | n/a
revisions 2 | included | 1 | 60 | 3 | n/a
DIGITAL DESIGN COMPONENT
website design (all pages) | no | 5 | 60 | 20 | 1200
design for on-line store | no | 1 | 60 | 10 | 600
design for scheduling tables | no | 1 | 60 | 6 | 360
copy (content, text) | no | 1 | 60 | 10 | 600
providing copy (contract out?) | no | 1 | 60 | 10 | 600
copy editing/proofreading | no | 1 | 60 | 6 | 360
number of images - provided | yes | 12 | n/a | n/a | n/a
image retouch | no | 12 | 70 | 12 | 840
photography provided | no |  | 60
photography needed (contract?) | no |  | 60
GRAPHIC DESIGN COMPONENT
brand identity (logo, colour palette, fonts, any brand graphics, stationery) (contract out?) | no | 1 | 100 | 40 | 4000
copywriting (mission, tagline) (contract out?) | no | 1 | 70 | 10 | 700
design of print ads | no | 4 | 60 | 12 | 720
revisions 1 | included
revisions 2 | included
additional revisions | no | 1 | 60 | 10 | 600
TOTAL |  | 62 |  |  | 17180