## Sheet1
PROJECT NAME: WEBSITE
CLIENT: Carolina Becerra - "Do Everything Salon" - Scenario 1
DATE: March 18, 2013
ADMINISTRATION | ESTIMATED HOURS | ACTUAL HOURS | DAYS - 8 hours
Initial meeting | 2
Meeting 2 | 1.5
Meeting 3 | 1.5
Meeting 4 | 1.5
Final Presentation | 1.5
Estimating | 3
Estimating contractors (contacting) | 3
Sending reports (meeting recaps) | 4
Billing | 2
SUBTOTAL: administration | 20 | 0 | 0
DIGITAL & GRAPHIC DESIGN COMPONENTS | EXISTING | QUANTITY | HOURLY RATE | ESTIMATED HOURS | ESTIMATED COST | DAYS - 8 hours | ACTUAL HOURS | BILLED | DAYS - 8 hours
Research | yes and no | 1 | 60 | 16 | 960
SUBTOTAL: digital & graphic design components |  |  |  | 16 | 960
DIGITAL COMPONENT | EXISTING | QUANTITY | HOURLY RATE | ESTIMATED HOURS | ESTIMATED COST | DAYS - 8 hours | ACTUAL HOURS | BILLED | DAYS - 8 hours
Information architecture | no | 1 | 60 | 8 | 480
Researching URL (client could take this on) | no | 1 | 60 | 1 | 60
Register URL (client could take this on) | no | 1 | 60 | 1 | 60
Securing URL | no | 1 | 60 | 1 | 60
Securing Service Provider | no | 1 | 60 | 1 | 60
Negotiating hosting rates | no | 1 | 60 | 3 | 180
Data base management (dedicated person) | no | 1 | 60 | 6 | 360
Data base compilation (dedicated person) | no | 1 | 60 | 4 | 240
Sourcing template | no | 1 | 60 | 4 | 240
Any additional custom coding | no | 1 | 60 | 20 | 1200
User testing | no | 1 | 60 | 8 | 480
Online shopping back end, including shopping cart check-out (Phase 2) | no | 1 | 60 | 8 | 480
Virtual makeover back end (Phase 2) | no | 1 | 60 | 10 | 600
Appointment booking back end (Phase 2) | no | 1 | 60 | 4 | 240
Email form back end (Phase 2) | no | 1 | 60 | 4 | 240
Revisions 1 | no | 1 | 60 | 6 | 360
Revisions 2 | no | 1 | 60 | 4 | 240
SUBTOTAL: digital component |  |  |  | 93 | 5580 | 0 | 0 | 0 | 0
DIGITAL DESIGN COMPONENT
Landing page (temporary "splash" page) | no | 1 | 60 | 8 | 480
Website template design | no | 5 | 60 | 24 | 1440
Design of online shopping page (Phase 2) | no | 1 | 60 | 8 | 480
Design of virtual makeover (Phase 2) | no | 1 | 60 | 10 | 600
Design of online appointment booking (Phase 2) | no | 1 | 60 | 8 | 480
Design of email form (Phase 2) | no | 1 | 60 | 4 | 240
Copywriting - contract out | no | 1 | 60 | 12 | 720
Copy editing/proofreading | no | 1 | 50 | 4 | 200
Images | yes | 12 | 60 | n/a | n/a
Image retouching or resizing | no | 12 | 60 | 8 | 480
SUBTOTAL: digital design component |  |  |  | 78 | 5120 | 0 | 0 | 0 | 0
GRAPHIC DESIGN COMPONENT
Brand identity (logo, colour palette, fonts, any brand graphics, stationery) | no | 1 | 90 | 65 | 5850
Copywriting (mission, tagline) | no | 1 | 65 | n/a | n/a
Revisions 1 | no | n/a | n/a | n/a | n/a
Revisions 2 | no | n/a | n/a | n/a | n/a
SUBTOTAL: graphic design component |  |  |  | 65 | 5850 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 252 | 17510